## Roles & Responsibilities
Role |  | Responsibility
Design | The designer's role is to collaborate closely with the development team and stakeholders to understand user needs, business goals, and project requirements. During sprint planning, the designer actively contributes to the creation of user stories and acceptance criteria, utilizing their expertise in UX and UI design to develop intuitive and visually appealing designs. They conduct user research, analyze feedback, and consider industry best practices to inform their design decisions. The designer also ensures the usability and accessibility of the product by conducting usability testing and adhering to accessibility guidelines. Throughout the sprint plan, they collaborate with the development team, providing support and clarifications as needed, to ensure accurate implementation of the designs and address any design-related issues that may arise.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Development | The developer's role is to collaborate closely with the team to understand the project requirements and design specifications. During sprint planning, the developer actively participates in discussions to grasp the user stories, acceptance criteria, and technical requirements. Their primary responsibility is to write clean, efficient, and maintainable code that aligns with the project's objectives. They work closely with the designer to accurately implement the designs and address any technical challenges. The developer conducts thorough testing to identify and fix bugs or issues, collaborating with the quality assurance team to ensure the software meets the defined acceptance criteria. They actively participate in code reviews, providing feedback to peers to promote code quality and adherence to standards. Throughout the sprint plan, the developer collaborates with the team, providing support and updates, and works closely with stakeholders to ensure the software solution meets the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Coding | The coder/modeler's role is to collaborate closely with the team to understand the project requirements, data sources, and technical specifications. During sprint planning, the coder/modeler actively participates in discussions to grasp the project's objectives. Their primary responsibility is to design and implement software models that utilize machine learning, artificial intelligence, or other advanced techniques to analyze and interpret data. They ensure the models are accurate, efficient, and scalable, utilizing their expertise in programming languages, data analysis, and modeling. The coder/modeler also ensures the models are properly integrated with the data infrastructure, working closely with the data engineer. They collaborate with the quality assurance team to ensure the models meet the defined acceptance criteria and pass all necessary tests. The coder/modeler also provides feedback to peers during code reviews, promoting code quality and adherence to standards. Throughout the sprint plan, they collaborate with the team, provide support, and work closely with stakeholders to ensure the software models meet the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Engineering | The data engineer's role is to collaborate closely with the team to design, build, and maintain the data pipelines required for the project. During sprint planning, the data engineer actively participates in discussions to understand the project requirements, data sources, and technical specifications. Their primary responsibility is to design and implement data pipelines that extract, transform, and load data from various sources into the project's data warehouse or data lake. They ensure the data is accurate, consistent, and accessible, utilizing their expertise in data modeling, database design, and data integration. The data engineer also ensures the security, privacy, and compliance of the data infrastructure, collaborating with the security and compliance teams to implement appropriate measures. Throughout the sprint plan, they collaborate with the team, provide support, and work closely with stakeholders to ensure the data infrastructure meets the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:

## Project Sprint Plan
Vendor Health PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  |  |  | PROJECT DELIVERABLE |  | STATUS KEY
| Vendor Health Platform Support |  |  |  | 2024-06-26 | 2024-12-31 | 188 |  |  |  | Vendor Health platform |  | COMPLETE
| PROJECT MANAGER | [9 empty] | SCOPE STATEMENT |  | ON HOLD
| Monica G, Danielson | [11 empty] | IN PROGRESS
| TASK NAME | FEATURE TYPE | RESPONSIBLE | # STORY POINTS | START | FINISH | DAYS | ACTUAL START | ACTUAL END | STATUS | STORY POINTS | Dependancy on DE Team | Requirements | Risk
Sprint 1: Mock up Design | Sprint 1: Mock up Design |  |  | 27 | 2024-07-09 |  |  |  |  | In Progress |  |  |  |  | Sprint 1: Mock up Design
Feature 1: Home Page Filter, Toggle, Tesla Dataset, Go Button | Feature 1: Home Page | Design | SriVishnu | 4 | 2024-07-09 | 2024-07-12 | 4 |  |  | Complete | Filter, Toggle, Tesla Dataset, Go Button | No |  |  | Feature 1: Home Page Filter, Toggle, Tesla Dataset, Go Button
Feature 2: Study/Program PageFilter, Expand Button, Download Button, Trending Date and Protocol Graph, Summary Details Table, User Manual, Information and Home Button | Feature 2: Study/Program Page |  |  | 10 | 2024-07-15 | 2024-07-26 | 10 |  |  | Complete | Filter, Expand Button, Download Button, Trending Date and Protocol Graph, Summary Details Table, User Manual, Information and Home Button |  |  |  | Feature 2: Study/Program PageFilter, Expand Button, Download Button, Trending Date and Protocol Graph, Summary Details Table, User Manual, Information and Home Button
| Feature 3: Portfolio Study/Program Page |  |  | 1 | 2024-07-29 | 2024-08-01 | 4 |  |  | Complete | Trending Date and Protocol Graph and table
| Feature 4: Portfolio General Page |  |  | 1 | 2024-08-02 | 2024-08-06 | 3 |  |  | Complete | Trending Date Graph and table
| Feature 5: Portfolio Therapeutic Area Page |  |  | 1 | 2024-08-07 | 2024-08-12 | 4 |  |  | Complete | Trending Date and Therapeutic Area Graph and table
| Feature 6: Portfolio Study Priority Page |  |  | 1 | 2024-08-13 | 2024-08-19 | 5 |  |  | Complete | Trending Date and Study Priority Graph and table
| Feature 7: Portfolio Vendor Page |  |  | 1 | 2024-08-20 | 2024-08-23 | 4 |  |  | Complete | Trending Date and Vendor Graph and table
| Feature 8: Portfolio 12 Month Data View Page |  |  | 1 | 2024-08-26 | 2024-08-29 | 4 |  |  | Complete | 12 Month Data View Table
| Feature 9: Tesla Portfolio Page |  |  | 3 | 2024-08-30 | 2024-09-06 | 6 |  |  | Complete | Filter, Quarter and Month Graph
| Feature 10: Tesla Open 30 Days Page |  |  | 1 | 2024-09-09 | 2024-09-12 | 4 |  |  | Complete | Donut Chart and two Bar Charts
| Feature 11: Tesla Category View Page |  |  | 1 | 2024-09-13 | 2024-09-17 | 3 |  |  | Complete | Gauge Chart, Bar Chart and Table
| Feature 12: Tesla Is An Issue Page |  |  | 1 | 2024-09-18 | 2024-09-20 | 3 |  |  | Complete | Filters and Table
| Feature 13: Tesla Report Data |  |  | 1 | 2024-09-23 |  |  |  |  | In Progress | Table
| Sprint 2: Set Up the Environment |  |  |  | 2024-09-25 |  |  |  |  | NOT STARTED
| Feature 1: Power BI Service Access | Development | Avinash, Rajesh | [6 empty] | NOT STARTED | Task - Raise ticket to get Power BI Service License | Yes
| Feature 2: Smartsheet Access | [8 empty] | NOT STARTED | Task 1 - Raise access to establish connection to the smartsheet | Yes
[10 empty] | NOT STARTED | Task 2 - Establishing API Connection to fetch data from the Smartsheet | Yes
| Feature 3: Data Understanding | [8 empty] | NOT STARTED | Task - Get the data understanding from stakeholder | Yes
| Feature 4: Perform Data Modelling | [8 empty] | NOT STARTED | Task 1 - Establishing relation between different tables while joining | No
[10 empty] | NOT STARTED | Task 2 - Creating bridge table | No
[10 empty] | NOT STARTED | Task 3 - Writing m queries | No
| Feature 5: Feasibility check | [8 empty] | NOT STARTED | Task 1 - Build the UI as per the wireframe - Layout | No
[10 empty] | NOT STARTED | Task 2 - Navigation | No
[10 empty] | NOT STARTED | Task 3 - Buttons and Tabs | No
[10 empty] | NOT STARTED | Task 4 - Graphs and Charts | No
[10 empty] | NOT STARTED | Task 5 - Feasibility check to ensure the charts outlined in the wireframe can be implemented in Power BI | Yes | Coordinate with the DE team to assess the possibility of using marketplace charts as alternatives to the default Power BI visualizations
[10 empty] | NOT STARTED | Task 6 - Establish a method for connecting Power BI to Tesla's Data | No
Sprint 3: Connecting to Smartsheet | Sprint 3: Connecting to Smartsheet |  |  |  | 2024-09-25 |  |  |  |  | NOT STARTED |  |  |  |  | Sprint 3: Connecting to Smartsheet
| Feature 1: | Development | Avinash |  | 2024-09-25 | 2024-09-26 |  |  |  | NOT STARTED |  | Yes
[5 empty] | 2024-09-27 | 2024-10-01 |  |  |  | NOT STARTED
[5 empty] | 2024-10-02 | 2024-10-04 |  |  |  | NOT STARTED
[5 empty] | 2024-10-07 | 2024-10-08 |  |  |  | NOT STARTED
Feature 2:Description 1 | Feature 2: |  | Avinash |  | 2024-10-08 | 2024-10-09 |  |  |  | NOT STARTED | Description 1 |  |  |  | Feature 2:Description 1
|  |  | Avinash |  | 2024-10-09 | 2024-10-10 |  |  |  | NOT STARTED | Description 2
Description 3 |  |  | Avinash |  | 2024-10-10 | 2024-10-11 |  |  |  | NOT STARTED | Description 3 |  |  |  | Description 3
Sprint 3: SPRINT NAME | Sprint 3: SPRINT NAME |  |  |  | 2024-05-20 | 2024-05-31 |  |  |  | NOT STARTED |  |  |  |  | Sprint 3: SPRINT NAME
Feature 1: Description 1 | Feature 1: |  | Avinash |  | 2024-05-20 | 2024-05-20 |  |  |  | NOT STARTED | Description 1 |  |  |  | Feature 1: Description 1
Description 2 |  |  | Avinash |  | 2024-05-20 | 2024-05-20 |  |  |  | NOT STARTED | Description 2 |  |  |  | Description 2
Feature 2: Description 1 | Feature 2: |  | Avinash |  | 2024-05-21 | 2024-05-21 |  |  |  | NOT STARTED | Description 1 |  |  |  | Feature 2: Description 1
Description 2 |  |  | Avinash |  | 2024-05-21 | 2024-05-21 |  |  |  | NOT STARTED | Description 2 |  |  |  | Description 2
|  |  | Avinash |  | 2024-05-21 | 2024-05-21 |  |  |  | NOT STARTED | Description 3
Sprint 4: SPRINT NAME | Sprint 4: SPRINT NAME |  |  |  | 2024-06-03 | 2024-06-14 |  |  |  | NOT STARTED |  |  |  |  | Sprint 4: SPRINT NAME
| Feature 1: |  | Avinash |  | 2024-06-04 | 2024-06-04 |  |  |  | NOT STARTED | Description 1
|  |  | Avinash |  | 2024-06-04 | 2024-06-05 |  |  |  | NOT STARTED | Description 2
|  |  | Avinash |  | 2024-06-05 | 2024-06-05 |  |  |  | NOT STARTED | Description 3
|  |  | Avinash |  | 2024-06-04 | 2024-06-04 |  |  |  | NOT STARTED | Description 4
| Feature 2: |  | Avinash |  | 2024-06-11 | 2024-06-11 |  |  |  | NOT STARTED | Description 1
|  |  | Avinash |  | 2024-06-11 | 2024-06-11 |  |  |  | NOT STARTED | Description 2
|  |  | Avinash |  | 2024-06-12 | 2024-06-12 |  |  |  | NOT STARTED | Description 3
Sprint 5: SPRINT NAME | Sprint 5: SPRINT NAME |  |  |  | 2024-06-17 | 2024-06-28 |  |  |  | NOT STARTED |  |  |  |  | Sprint 5: SPRINT NAME
| Feature 1: |  |  |  | 2024-06-17 | 2024-06-18 |  |  |  | NOT STARTED | Description 1
| Feature 2: |  |  |  | 2024-06-17 | 2024-06-18 |  |  |  | NOT STARTED | Description 1
[5 empty] | 2024-06-18 | 2024-06-20 |  |  |  | NOT STARTED | Description 2
[5 empty] | 2024-06-18 | 2024-06-20 |  |  |  | NOT STARTED | Description 3
Sprint 6: SPRINT NAME | Sprint 6: SPRINT NAME |  |  |  | 2024-07-01 | 2024-07-12 |  |  |  | NOT STARTED |  |  |  |  | Sprint 6: SPRINT NAME
| Feature 1: |  |  |  | 2024-07-01 | 2024-07-02 |  |  |  | NOT STARTED | Description 1
[5 empty] | 2024-07-09 | 2024-07-10 |  |  |  | NOT STARTED | Description 2
[5 empty] | 2024-07-10 | 2024-07-12 |  |  |  | NOT STARTED | Description 3
| Feature 2: |  |  |  | 2024-07-01 | 2024-07-01 |  |  |  | NOT STARTED | Description 1
[5 empty] | 2024-07-05 | 2024-07-09 |  |  |  | NOT STARTED | Description 2
[5 empty] | 2024-07-08 | 2024-07-09 |  |  |  | NOT STARTED | Description 3
#REF! | Sprint 7: SPRINT NAME |  |  |  | 2024-07-15 | 2024-07-26 |  |  |  | NOT STARTED
| Feature 1: |  |  |  | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 1
[5 empty] | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 2
[5 empty] | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 3
[5 empty] | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 4
[5 empty] | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 5
#REF! | Feature 2: |  |  |  | 2024-07-16 | 2024-07-16 |  |  |  | NOT STARTED | Description 1
#REF! | Sprint 8: SPRINT NAME |  |  |  | 2024-07-15 | 2024-07-26 |  |  |  | NOT STARTED
#REF! | Feature 1: |  |  |  | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 1
#REF! | Feature 2: |  |  |  | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 1
#REF! |  |  |  |  | 2024-07-15 | 2024-07-19 |  |  |  | NOT STARTED | Description 2
#REF! | Sprint 9: SPRINT NAME |  |  |  | 2024-06-27 | 2024-07-10 |  |  |  | NOT STARTED
| Feature 1: |  |  |  | 2024-06-27 | 2024-07-10 |  |  |  | NOT STARTED | Description 1
[5 empty] | 2024-06-25 | 2024-07-10 |  |  |  | NOT STARTED | Description 2
[5 empty] | 2024-06-20 | 2024-07-10 |  |  |  | NOT STARTED | Description 3
[5 empty] | 2024-06-27 | 2024-07-10 |  |  |  | NOT STARTED | Description 4
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.

## Lists (hidden)
Design | Yes | Complete
Development | No | On-Hold
Engineering |  | In Progress
Coding |  | Not Started