## Roles & Responsibilities
Role |  | Responsibility
Design | The designer's role is to collaborate closely with the development team and stakeholders to understand user needs, business goals, and project requirements. During sprint planning, the designer actively contributes to the creation of user stories and acceptance criteria, utilizing their expertise in UX and UI design to develop intuitive and visually appealing designs. They conduct user research, analyze feedback, and consider industry best practices to inform their design decisions. The designer also ensures the usability and accessibility of the product by conducting usability testing and adhering to accessibility guidelines. Throughout the sprint plan, they collaborate with the development team, providing support and clarifications as needed, to ensure accurate implementation of the designs and address any design-related issues that may arise.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Development | The developer's role is to collaborate closely with the team to understand the project requirements and design specifications. During sprint planning, the developer actively participates in discussions to grasp the user stories, acceptance criteria, and technical requirements. Their primary responsibility is to write clean, efficient, and maintainable code that aligns with the project's objectives. They work closely with the designer to accurately implement the designs and address any technical challenges. The developer conducts thorough testing to identify and fix bugs or issues, collaborating with the quality assurance team to ensure the software meets the defined acceptance criteria. They actively participate in code reviews, providing feedback to peers to promote code quality and adherence to standards. Throughout the sprint plan, the developer collaborates with the team, providing support and updates, and works closely with stakeholders to ensure the software solution meets the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Coding | The coder/modeler's role is to collaborate closely with the team to understand the project requirements, data sources, and technical specifications. During sprint planning, the coder/modeler actively participates in discussions to grasp the project's objectives. Their primary responsibility is to design and implement software models that utilize machine learning, artificial intelligence, or other advanced techniques to analyze and interpret data. They ensure the models are accurate, efficient, and scalable, utilizing their expertise in programming languages, data analysis, and modeling. The coder/modeler also ensures the models are properly integrated with the data infrastructure, working closely with the data engineer. They collaborate with the quality assurance team to ensure the models meet the defined acceptance criteria and pass all necessary tests. The coder/modeler also provides feedback to peers during code reviews, promoting code quality and adherence to standards. Throughout the sprint plan, they collaborate with the team, provide support, and work closely with stakeholders to ensure the software models meet the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:
Engineering | The data engineer's role is to collaborate closely with the team to design, build, and maintain the data pipelines required for the project. During sprint planning, the data engineer actively participates in discussions to understand the project requirements, data sources, and technical specifications. Their primary responsibility is to design and implement data pipelines that extract, transform, and load data from various sources into the project's data warehouse or data lake. They ensure the data is accurate, consistent, and accessible, utilizing their expertise in data modeling, database design, and data integration. The data engineer also ensures the security, privacy, and compliance of the data infrastructure, collaborating with the security and compliance teams to implement appropriate measures. Throughout the sprint plan, they collaborate with the team, provide support, and work closely with stakeholders to ensure the data infrastructure meets the project's requirements and goals.
Specific Responsibility #1:
Specific Responsibility #2:
Specific Responsibility #3:

## Project Sprint Plan
ATOMS PROJECT SPRINT
| PROJECT NAME |  |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  |  |  | PROJECT DELIVERABLE |  | STATUS KEY
| ATOMS | [9 empty] | Landing Page of Atoms |  | COMPLETE
| PROJECT MANAGER | [9 empty] | SCOPE STATEMENT |  | ON HOLD
| Shanmugha Priya | [9 empty] | Develop Landing page of Atoms on Spotfire |  | IN PROGRESS
| TASK NAME | ROLE | RESPONSIBLE | # STORY POINTS | START | FINISH | ACTUAL START DATE | ACTUAL FINISH DATE | DAYS | STATUS | STORY POINTS | Dependancy on Priya | Requirements | Risk
Sprint 1: Landing Page Development | Sprint 1: Landing Page Development |  |  |  | 2024-09-19 | Tentative |  |  |  | In Progress |  |  |  |  | Sprint 1: Landing Page Development
Feature 1: Redesigned Hexagon ChartsModified layout of hexagons in home page | Feature 1: Redesigned Hexagon Charts | Design |  | 1 | [5 empty] | Complete | Modified layout of hexagons in home page |  |  |  | Feature 1: Redesigned Hexagon ChartsModified layout of hexagons in home page
| Feature 2: Development of layout of landing page | Development |  | 8 | [5 empty] | Complete | Development of main layout
[10 empty] | Complete | Download all images as svgs
[10 empty] | Complete | Development of header(logos, project title, icons like contact, info)
[10 empty] | Complete | Development of sub-header (home button, dropdown)
[10 empty] | Complete | Development of KPIs section
[10 empty] | Complete | Development of content section
[8 empty] | 2024-09-25 |  | Complete | Removal of user guide icon
[8 empty] | 2024-09-25 |  | Complete | Addition of contact links | Yes | Require Contact Links
| Feature 3: Development of Modal UI | Development |  | 2 |  |  |  | 2024-09-25 |  | Complete | Development of modal
[8 empty] | 2024-09-25 |  | Complete | Add functionality ( clicking on info icon, show the modal )
| Feature 4: Development of Hexagon Charts UI | Development |  | 2 |  |  |  | 2024-09-25 |  | Complete | Development of hexagon charts in UI using D3
[8 empty] | 2024-09-25 |  | Complete | Updating colors of hexagons on click
| Feature 5: Actual Data Integration | Development |  | 1 | [6 empty] | Transform data into required data structure | Yes | Require actual data
| Feature 6: Add functionality for Hexagon Charts | Development |  | 2 | [6 empty] | Update KPI Section counts based on the selected organ
Navigation to algorithm page on clicking algorithm name
| Feature 7: Development of Organ section | Development |  | 2 | [6 empty] | Appending organ's hexagon charts and human body image
Navigate back to home page on clicking organ's hexagon chart
| Feature 8: Development of Summary section | Development |  | 3 | [6 empty] | Add content and images in summary section
Development of dataset section dropdown
Populate dropdown with dataset names | [9 empty] | Not Started | Populate dropdown with dataset names |  |  |  | Populate dropdown with dataset names
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.

## Lists (hidden)
Design | Yes | Complete
Development | No | On-Hold
Engineering |  | In Progress
Coding |  | Not Started